# 6-Week Roadmap - Agentic Workflows App

Generated: 2026-03-05

Scope baseline: D:/source/prompts monorepo (agentic-workflows-v2, agentic-v2-eval, tools, docs, CI config).

# Roadmap Basis (Repo Signals)

Current shipped capability includes 10 YAML workflows, DAG execution, tiered model routing, FastAPI APIs, SSE/WebSocket streaming, and a React UI.

Backlog status in analysis/BACKLOG.md (updated 2026-03-05) shows major quick wins done, with remaining work concentrated in docs onboarding, cross-package integration testing, protocol typing hardening, and advanced agent quality loops.

CI currently enforces 70% coverage in .github/workflows/ci.yml while the package target is 80%, so quality gates need staged tightening.

# Architecture Constraints to Respect

Dual-engine model: LangChain/LangGraph is the primary runtime path and native DAG remains a secondary engine. Changes must preserve adapter parity.

Monorepo package isolation: agentic-workflows-v2, agentic-v2-eval, and tools are intentionally independent, so integration confidence must come from end-to-end tests rather than direct imports.

Feature delivery depends on optional extras (langchain, server, rag, claude, tracing); environment drift is a practical risk for dev and CI parity.

Workflow DSL has duplicated iterative sections (notably deep_research rounds), so iterate-style improvements must stay backward-compatible with existing YAML definitions.

# Milestones

Milestone 1 (end of Week 2): Foundation and DX uplift complete. Onboarding docs, workflow authoring guidance, pattern catalog, and CI hygiene improvements are merged.

Milestone 2 (end of Week 4): Architecture hardening complete. Protocol typing tightened, cross-package integration test spine running in CI, and retrieval quality baseline improved with reranking experiments.

Milestone 3 (end of Week 6): Intelligence and maintainability release candidate. Reflection loop, evaluation feedback hooks, DSL iteration improvements, and high-risk codebase cleanup delivered.

# Week-by-Week Plan

| Week | Primary goal | Deliverables | Exit criteria |
| --- | --- | --- | --- |
| Week 1 | Baseline hardening and execution hygiene | Implement CI updates for tools/eval test jobs; enforce docs reference checks; add issue/PR templates and concept glossary. | CI runs all core package test suites; docs/link checks are blocking; contribution templates live. |
| Week 2 | Developer onboarding and workflow documentation | Ship docs/ONBOARDING.md, workflow authoring guide, and pattern catalog; add 2-3 practical examples (RAG, custom agent, workflow authoring). | New contributor can run first workflow and first evaluation from docs without manual intervention. |
| Week 3 | Protocol and integration test hardening | Tighten Any-heavy protocol signatures with bounded types where practical; add cross-package integration tests (tools -> engine -> eval). | Protocol conformance tests pass and integration suite is stable in CI. |
| Week 4 | Retrieval quality and quality-gate ratchet | Add reranking prototype behind feature flag; benchmark against current RRF-only retrieval; raise coverage gate toward 80% with targeted test additions. | Benchmark report published and CI gate raised with no persistent red builds. |
| Week 5 | Agent self-correction and feedback wiring | Implement BaseAgent reflection/revise loop behind config toggle; connect evaluation signals to execution feedback hooks (phase 1). | Controlled A/B runs show quality uplift or a clear stop/go decision with latency and cost data. |
| Week 6 | DSL and maintainability consolidation | Introduce iterate-style workflow construct (or equivalent de-dup mechanism) for repeated deep_research rounds; modernize targeted tools modules and split one oversized hotspot file. | Release candidate branch cut with migration notes, risk log closure, and rollback path. |

# Dependencies

Consistent CI runners and dependency extras installation for all package paths (dev/server/langchain/rag/claude as needed).

Model/API credentials and evaluation datasets available in non-production test environments for benchmark weeks.

Dedicated maintainer time each week for architecture review plus one docs-focused reviewer for onboarding outputs.

Stable benchmark harness and representative workloads to evaluate reranking and reflection changes objectively.

# Risks and Mitigations

Risk: Dual-engine behavioral drift when protocol signatures change. Mitigation: adapter contract tests must run for both native and LangChain paths before merge.

Risk: CI instability from added suites and higher coverage gate. Mitigation: ratchet thresholds in staged increments and track flaky tests weekly.

Risk: Reranking and reflection loops increase latency/cost. Mitigation: ship behind toggles with explicit budget limits and benchmark-based go/no-go criteria.

Risk: DSL iterate changes break existing workflows. Mitigation: preserve backward compatibility and include fixture-based migration tests for all 10 shipped workflows.

Risk: Scope overload across docs + architecture + ML enhancements in 6 weeks. Mitigation: enforce milestone gates and defer lower-value backlog items when exit criteria are at risk.

# Definition of Done for Week 6

All Week 1-6 exit criteria met or explicitly re-scoped with documented rationale.

Open high-severity risks have owners and dated mitigation plans.

Roadmap outcomes are reflected in analysis/BACKLOG.md statuses and linked PRs.